## EXAMPLE - Budget Contingency
Percentage-Based Budget Contingency Template
[6 empty] | CONTINGENCY PERCENTAGE |  | TOTAL BUDGET |  | CONTINGENCY BUDGET |  | TOTAL BUDGET with CONTINGENCY
[6 empty] | 7.5% |  | 22784.35 |  | 1708.8262 |  | 24493.1762
User to complete non-shaded cells only. | [5 empty] | LABOR |  |  | MATERIALS |  |  | FIXED
TASK | DESCRIPTION | STATUS | PLANNED START DATE | ACTUAL START DATE | END DATE | HR | $/HR | TOTAL LABOR | UNITS | $/UNITS | TOTAL MATERIALS | TRAVEL | EQUIPMENT / SPACE | MISC. | TOTAL
Task |  | Complete |  |  |  | 40 | 40 | 1600 | 12 | 15 | 180 | 500 | 600 | 50 | 2930
Task |  | In Progress |  |  |  | 4 | 40 | 160 | 12 | 15 | 180 | 500 | 600 | 50 | 1490
Task |  | Overdue |  |  |  | 8 | 15 | 120 | 22 | 14 | 308 | 200 | 600 | 100 | 1328
Task |  | In Progress | [5 empty] | 0 | 50 | 11 | 550 |  |  | 300 | 850
Subtask |  | Needs Review |  |  |  | 6 | 10 | 60 | 44 | 45 | 1980 |  |  |  | 2040
Subtask |  | Approved | [5 empty] | 0 | 3 | 500 | 1500 |  |  | 7500 | 9000
Subtask |  | Not Started | [5 empty] | 0 |  |  | 0 |  | 2200 |  | 2200
Subtask |  | On Hold | [5 empty] | 0 |  |  | 0 |  | 350 |  | 350
Task | [5 empty] | 10 | 65 | 650 | 13 | 68.95 | 896.35 |  |  |  | 1546.35
Task | [5 empty] | 5 | 120 | 600 |  |  | 0 |  |  | 450 | 1050
SUBTOTAL | [7 empty] | 3190 |  |  | 5594.35 | 1200 | 4350 | 8450 | 22784.35
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Budget Contingency
Percentage-Based Budget Contingency Template
[6 empty] | CONTINGENCY PERCENTAGE |  | TOTAL BUDGET |  | CONTINGENCY BUDGET |  | TOTAL BUDGET with CONTINGENCY
[6 empty] | 5% |  | 0 |  | 0 |  | 0
User to complete non-shaded cells only. | [5 empty] | LABOR |  |  | MATERIALS |  |  | FIXED
TASK | DESCRIPTION | STATUS | PLANNED START DATE | ACTUAL START DATE | END DATE | HR | $/HR | TOTAL LABOR | UNITS | $/UNITS | TOTAL MATERIALS | TRAVEL | EQUIPMENT / SPACE | MISC. | TOTAL
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
SUBTOTAL | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.